## Confidence Mapping
1. List stakeholder by influence over outcomes -- not by org chart
| Influence Over Outcomes | Stakeholder Segment
| Decision Power | Sponsors, steering committee
| Operational Power | Directors, frontline leaders
| Social Power | Culture carriers, informal influencers
| Customer Power | Key customer, partners
| Delivery Power | Product, IT, PMO
2. Score the four Confidence Drivers (average the first 3 for the confidence axis -- or weight how you see fit.
| Driver | What to score (1-5)
| Trust | Do they believe leadership can deliver?
| Value | Do they see the change as worth the effort and expense?
| Advocacy | Will they actively support and reinforce it?
| Capacity | Do they have the bandwidth to absorb it now?
3. Plot the confidence map, Diagnose the risk and Target the Leadership action
| Zone | Leadership Actions
| Momentum | Amplify Wins; Equip advocates; Use visable proof points
| Burnout Risk | Reduce competing demands; Add support
| Political Risk | Increase sponsor visibility; sharpen messaging; address belief gaps
| Failure Zone | Pause; Reset; or Redesign before more value is lost
Stakeholder Confidence
Political Risk
Failure Zone
Momentum Zone
Burnout Risk
Capacity Strain
High
High
Low
Low
Adoption working
Adoption breakdown
Confidence Problem
Align
Amplify
Protect
Reset
Stakeholder Confidence Map
Change Capacity

## CCA
CHANGE COMPLEXITY ASSESSMENT (CCA)
Project Number & Name
Project Description | Provide brief overview of initiative
Instructions | Select a score in the "Score" column, based on the rating (level 1-5) that best describes your change initiative for each element.
Element | Definition | Ratings |  |  |  |  | Score | Rationale / Comments
|  | 1 | 2 | 3 | 4 | 5
Change Magnitude Weight or degree of the change | How simple or complex the change is in terms of project scope, change type, impact on and value to the organization. | Low Magnitude · Small adjustments, incremental improvements · Minimal disruption to business operations |  | Moderate Magnitude · Moderate changes to business tools, processes, or systems |  | High Magnitude · Large-scale, transformational shifts that significantly impact the organization's strategy, structure, culture, or technology
Organizational Complexity Who's impacted and how? | How far the change extends across teams, functions, geographies-- and the variance of the impacts across those stakeholders. | Low Complexity · Low number of impacted stakeholders · Low variance in change impacts across impacted stakeholders |  | Moderate Complexity · Impacts several functions or business units with minimal variance among stakeholders · Impacts a small number of stakeholder groups and has medium variance in the impacts |  | High Complexity · Enterprise-wide or global impact · Stakeholders are from multiple, diverse groups (departments, roles, locations) · High variance in change impacts across impacted stakeholders
Stakeholder Engagement Effort to engage and align | The level of effort needed to engage people, secure buy-in and manage the responses from individuals or groups impacted by or critical to the success of the change. | Low Effort · Impacted stakeholders expected to support the change · Minimal competing priorities |  | Moderate Effort · Impacted stakeholders are neutral towards the change · Some competing priorities |  | High Effort · Significant effort to secure buy-in · Numerous competing priorities
Adoption Support Capability Building | The level of learning and enablement required for impacted stakeholders to adopt and integrate new tools, processes, or ways of working to succeed in the new environment. | Minimal Support · Little to no enablement required for impacted stakeholders to successfully adopt the change - Minimal enablement modalities / vehicles |  | Moderate Support · Moderate enablement is required for impacted stakeholders to successsfully adopt the change · Limited enablement modalities / vehicles |  | Comprehensive Support · Extensive and sustained enablement required for impacted stakeholders to successfully adopt the change · Numerous and varied enablement modalities / vehicles
External Customer Impact | The level of impact and visibility of the change to customers and the level of communication, support, and relationship management required to adapt to and adopt the changes. | Low Impact · Minimal external customer impact · Internal-only change = 0 |  | Moderate Impact · Some external customer impact · Moderate change to occasionally performed interactions |  | High Impact · Significant external customer impact · High value customers could be impacted · Significant change to important or regularly performed interactions
[6 empty] | Total | 0
|  | Score | Complexity Rating | Expected Change Management Resourcing Pathway
|  | 7 to 16 | Low | Self Help | The assessment suggests that the change management effort is straight-forward and manageable with minimal risk. Due to the low change complexity, no dedicated change management resource will be assigned to the project. Guidance, resources and templates are available to assist with any change management needs on the CCOE SharePoint site.
|  | 17 to 24 | Medium | Trusted Advisor | The assessment suggests that the required change management effort would benefit from a change management resource support to consult and advise the project lead on change management approach based on the project specifics. Project Sponsor commitment is expected to support change awareness, adoption and reinforcement. Plan to have a dedicated business resource to support change efforts.
|  | 25 to 35 | High | Dedicated Change Leader | The assessment suggests that the initiative will require a comprehensive change management effort. It is recommended that the project engage a dedicated change management resource to conduct detailed assessments, design and deliver a suitable change management approach.

## CCA Prompts
Change Magnitude | Organizational Complexity | Stakeholder Engagement | Adoption Support | External Customer Impact
How simple or complex the change is in terms of project scope, change type, impact on and value to the organization. | How far the change extends across teams, functions, geographies-- and the variance of the impacts across those stakeholders. | The level of effort needed to engage people, secure buy-in and manage the responses from individuals or groups impacted by or critical to the success of the change. | The level of learning and enablement required for impacted stakeholders to adopt and integrate new tools, processes, or ways of working to succeed in the new environment. | The level of impact and visibility of the change to customers and the level of communication, support, and relationship management required to adapt to and adopt the changes.
What is changing? | How many business units/groups/departments does this change impact? | What is the perception of this change by impacted stakeholders? | What will impacted stakeholders have to do differently as a result of this change? | What impact does this project have on external customers?
What is the current state? What is the desired future state? | How related are these impacted groups? (team, function, location) | Does perception vary by stakeholder group? Job role? Tenure? Identity? Values? Etc. | What training/coaching/information is required for stakeholders to build the knowledge/ability to adapt to the change? | What will these customers have to do differently because of this change?
What is the timeframe for implementation? | How varied is the impact across these stakeholder groups? | Are these stakeholders aware of how this change fits into the wider organizational strategy/big picture? | Does this impact their regularly performed work or occasionally performed actions? | What is required for customers to build the knowledge & ability to adapt to the change?
What is the implementation approach? (phased/big bang) |  | Is this change reducing, maintaining or adding to their currently workload? | Is this a mandated or optional change? | What are the impacts on customers if this project is not implemented successfully?
Will there be a trial phase ahead of the project launch? |  | How much change are those most impacted by this change currently experiencing/have recently experienced?
Is this a standalone project or part of larger initiative? |  | What projects, that could impact stakeholders, are going live at a similar time? | Enablement: Equipping people with the knowledge, skills, tools, and confidence they need to succeed.
What factors are driving this change? |  | How much trust does this group have in projects being implemented successfully?
What is the risk to the organization if this project is not implemented successfully?
Does the organization have recent experience implementing a similar project? |  | Engagement: Sparking interest, encouraging participation and building commitment.
Alignment: Getting everyone on the same page, with the same purpose, moving in the same direction.
Note on B4: What is changing? Business strategy? Organizational culture? Organizational structure? Change of Job responsibilities? Elimination of roles? Technology? Systems? Processes?
Note on E5: What support will stakeholders require? Communications? Wintrust University? In person learning? Coaching? Job aids? Playbooks? Coaching? IT tech support? Town halls & team meetings? Q&A sessions? HR Support?

## Adoption Metrics
Measuring Adoption Success (Adoption Metrics)
REACH | DEPTH | QUALITY | QUALITY (AND INFORMS ALL)
Usage (Baseline Adoption) | Depth of Adoption (Meaningful Use) | Quality of Adoption (Right Behaviors) | Support & Friction Signals
Are people using it at all? | Are they using it the right way? | Are they using it effectively and correctly? | Where is adoption breaking down?
Active User Rate: % of target population using the tool/process | Core Feature Utilization: % using critical functionality vs basic use | Error Rate / Exception Rate per User | Help Desk Tickets per User / per Feature
Login / Access Frequency: daily, weekly active users | End-to-End Process Completion Rate: not just starting, but finishing correctly | First-Time-Right Rate: % of transactions completed without rework | Top 3 Adoption Barriers (qualitative themes)
Feature Activation Rate: % who used at least 1 key feature | Manual Workaround Rates: shadow systems, offline tracking | Compliance to Standard Process | Training Completion vs. Usage Gap
Adoption by Role / Segment: lenders vs ops vs managers | Digital vs Legacy Channel Usage Mix | Decision Quality Indicators: if applicalbe--credit decisions approvals | Time Spent Seeking Help / Workarounds
REACH & SUSTAINABILITY | SUSTAINABILITY | SUSTAINABILITY | SUSTAINABILITY
Speed to Adoption (Time-Based Metrics) | Sustainability of Adoption | Manager Reinforcement (Big Differentiator) | Sentiment & Confidence (Leading Indicators)
How fast are we getting to value? | Does adoption stick -- or fade? | Are leaders driving adoption? | Will adoption continue to improve?
Time to First Use: post-training or go-live | Adoption Retention Rate: usage sustained over 30/60/90 days | % of Managers Conducting Reinforcement Activities: 1:1's, coaching | User Confidence Score: I feel XXXX using the new process / tool
Time to Proficiency: when users operate independently | Drop-off Rate After Initial Use | Frequency of Adoption Discussions in Team Meetings | Perceived Value Score: This helps me do my job better
Adoption Curve Velocity: rate of uptake over time | Reversion to Old Ways: % | Manager Adoption Scorecards Completed | Resistance Indicators: qualitative or survey-based
Time to Full Adoption Threshold: 80-90% | Repeat Usage / Habit Formation Indicators | Correlation: Manager Engagement vs Team Adoption | Change Fatigue Index (if tracked)

## Value Metrics
Driving Measurable Business Value (Value Metrics)
Revenue & Growth | Cost & Efficiency | Risk & Compliance
Time-to-Revenue: ↓20% | Cycle Time Reduction: -25% | Compliance Exceptions: -40%
Product Adoption: 88% active users | Employee Time Saved: +6 hrs/week/team | Standardized Process Adoption: 95%
Pipeline Conversion: +12% | Rework Reduction: -30% | Audit Findings: ↓trending
Customer Impact | Workforce Adoption (Leading Indicators) | Value Realization Tracker
CSAT: +10 pts | Active Usage: 92% | Value Leakage (Expected vs Realized Benefits)
Turnaround time: -18% | Manager Reinforcement: 85% | Expected Value: $12M
Complaints: -22% | Employee Confidence: improving trend ↑ | Realized Value: $10.5 M
Gap Closed: +15% YoY
Data Sources: Adoption analytics, employee surveys, operational KPIs, customer metrics

## Prosci Success Metrics
Link to Prosci Change Success Metrics Idea Generator: https://empower.prosci.com/change-success-metrics-idea-generator-dashboard?submissionGuid=52a54aa8-494b-4471-8abc-dd2384ca817b

## Sheet2 (hidden)
Self Help
Trusted Advisor
Dedicated Change Leader